## Emily
Date | Time In | Time Out | Description of Work | Total Time
2025-10-01 | 0.45833 | 0.64583 | Research on components, primarily microprocessor and camera sensor | 4
2025-10-02 | 0.58333 | 0.70833 | Research on similar projects and integration techniques | 3
2025-10-07 | 0.47917 | 0.5 | Check in meeting 1, discussed design draft | 0.5
2025-10-09 | 0.5 | 0.54167 | Discussion with team on feedback from design draft, ideas on how to implement | 1
2025-10-14 | 0.47917 | 0.52083 | Check in meeting 2, discussed improvements for final design plan | 0.5
2025-10-17 | 0.54167 | 0.625 | Team meeting, compiled research on possible components, discussed | 2 | 46
2025-10-23 | 0.47917 | 0.52083 | Check in meeting 3, reviewed possible parts list | 1
2025-10-23 | 0.66667 | 0.70833 | Reviewed tinkercad for pre alpha build | 1
2025-10-24 | 0.54167 | 0.66667 | Researched haptic feedback articles to address user friendliness | 3
2025-10-25 | 0.625 | 0.77083 | Created simple CNN for car detection | 3.5
2025-11-04 | 23:30 | 13:00 | Check in meeting 5, ordered Raspberry Pi, camera attachment for Raspberry Pi, and webcam in case; discussed plan to meet for Raspberry Pi and camera setup | 1.5
2025-11-07 | 13:00 | 16:00 | Gathered materials; set up Raspberry Pi and camera module; created simple script to make sure pictures/videos could be taken | 3
2025-11-11 | 12:30 | 16:00 | Met with team and emailed stakeholder in lieu of Check in meeting 6; trained and tested ML model for vehicle image dataset | 3.5
2025-11-13 | 23:00 | 15:30 | Met with team and started working on the Onshape prototype for the helmet attachment. | 4.5
2025-11-13 | 18:00 | 20:00 | Worked on the documentation for the Prototype Report | 2
2025-11-14 | 14:30 | 17:30 | continued working on the onshape prototype | 3
2025-11-15 | 11:00 | 15:00 | finished working on the OnShape Prototype | 4
2025-11-16 | 13:30 | 17:00 | Worked on the documentation for the Prototype Report | 3.5
2025-11-16 | 21:30 | 23:00 | Worked on the documentation for the Prototype Report | 1.5

## Gabriel
Date | Time In | Time Out | Description of Work | Time
2025-10-01 | 0.54167 | 0.66667 | Researched possible parts that can be used in our design | 3
2025-10-03 | 0.375 | 0.4375 | Looked into haptic sensors/piezos and what could fit our product | 1.5
2025-10-07 | 0.47917 | 0.5 | Check in meeting 1, discussed design draft | 0.5
2025-10-09 | 0.5 | 0.54167 | Discussion with team on feedback from design draft, ideas on how to implement | 1
2025-10-10 | 0.58333 | 0.70833 | Began studying ML via online tutorials and youtube videos | 3
2025-10-12 | 0.70833 | 0.75 | Researched different cameras that we could use for ML | 1
2025-10-14 | 0.47917 | 0.52083 | Check in meeting 2, discussed improvements for final design plan | 1 | Total Time
2025-10-15 | 0.70833 | 0.85417 | Continued studying basic ML for the camera portion of our design | 3.5
2025-10-17 | 0.54167 | 0.66667 | Team meeting, compiled research on possible components, discussed | 3 | 46.5
2025-10-20 | 0.66667 | 0.77083 | Further researched ML for camera vision | 2.5
2025-10-23 | 0.47917 | 0.52083 | Check in meeting 3, reviewed possible parts list | 1
2025-10-25 | 18:00 | 20:30 | Researched object detection examples in Raspberry Pi as well as pre-trained models (Tensorflow) | 2.5
2025-10-28 | 11:00 | 12:30 | Check in meeting 4; afterwards discussed purchase of components | 1.5
2025-11-02 | 17:00 | 19:00 | Meeting with team, discussed work assignments and researched technical work to be completed | 2
2025-11-04 | 11:00 | 12:30 | Check in meeting 5; ordered Raspberry Pi, camera, and haptic sensors | 1.5
2025-11-07 | 11:00 | 13:00 | Set up radar sensor with Arduino; got it to detect presence | 3
2025-11-07 | 13:00 | 16:00 | Set up Raspberry Pi OS, configured camera, and took photos and videos with it to assess functionality | 3
2025-11-11 | 13:00 | 16:00 | Met with team; mostly worked on configuring remote access to Raspberry Pi via SSH | 3
2025-11-13 | 0.48958 | 0.77083 | Configured object detection on camera and got it working | 6.75
2025-11-17 | 0.41667 | 0.51042 | Created script to automatically set up camera on new raspi images | 2.25

## Devika
Date | Time In | Time Out | Description of Work | Total Time
2025-10-01 | 0.45833 | 0.60417 | Research on components, primarily microprocessor and camera sensor | 3.5
2025-10-02 | 0.58333 | 0.70833 | Research on textbook about computer vision with Raspberry Pi, read some of book | 3
2025-10-07 | 0.47917 | 0.5 | Check in meeting 1, discussed design draft | 0.5
2025-10-09 | 0.5 | 0.54167 | Discussion with team on feedback from design draft, ideas on how to implement | 1
2025-10-14 | 0.47917 | 0.52083 | Check in meeting 2, discussed improvements for final design plan | 0.5
2025-10-17 | 0.54167 | 0.66667 | Team meeting, compiled research on possible components, discussed | 3 | Total Time:
2025-10-23 | 0.47917 | 0.52083 | Check in meeting 3, reviewed possible parts list | 1 | 47.25
2025-10-23 | 0.66667 | 0.70833 | Reviewed tinkercad for pre alpha build | 1
2025-10-24 | 0.54167 | 0.66667 | Researched and found Kaggle dataset for car detection, yolo code for image recognition | 3
2025-10-25 | 0.625 | 0.77083 | Created simple CNN for car detection | 3.5
2025-10-28 | 11:00 | 12:30 | Check in meeting 4, discussed with team after to purchase parts | 1.5
2025-11-02 | 17:00 | 19:00 | Meeting with team, discussed work assignments and researched technical work to be completed | 2
2025-11-04 | 11:00 | 12:30 | Check in meeting 5, ordered Raspberry Pi, camera, and haptic sensors | 1.5
2025-11-07 | 11:00 | 13:00 | Set up radar sensor with Arduino, wrote code to communicate through UART to detect presence | 3
2025-11-07 | 13:00 | 16:00 | Set up Raspberry Pi OS, configured camera, wrote Python script to record videos and take photos to prove camera functionality | 3
2025-11-09 | 19:00 | 22:00 | Updated the CNN, used a simpler architecture, wrote code to preprocess image dataset and trained model | 3
2025-11-11 | 10:00 | 11:30 | Wrote email in lieu of check in 6, updating professor on work the team completed and will present for prototype | 1.5
2025-11-11 | 13:00 | 16:00 | Met with team to continue working on prototype report, slides, and found example model to download on Raspberry Pi | 3
2025-11-11 | 17:00 | 19:00 | Researched converting Pytorch CNN model to tflite format for Raspberry Pi, started writing code to convert model | 2
2025-11-13 | 11:45 | 14:00 | Connected radar sensor to rest of sensors (LED, piezo, and haptic), updated Arduino code to have total interaction | 2.25
2025-11-13 | 14:00 | 15:30 | Updated Raspberry Pi OS to be compatible with popular ML models, downloaded example model for object detection | 1.5
2025-11-16 | 15:00 | 18:00 | Double checked functionality of Raspberry Pi with downloaded model, and radar sensor-piezo setup, practice demo | 3

## Janelle
Date | Start Time | End Time | Duration | Summary of Tasks Completed
2025-10-01 | 0.45833 | 0.60417 | 3.5 | Research on components, primarily microprocessor and camera sensor
2025-10-02 | 0.58333 | 0.70833 | 3 | Research on textbook about computer vision with Raspberry Pi
2025-10-07 | 0.47917 | 0.52083 | 1 | Check in meeting 1, discussed design draft
2025-10-09 | 0.5 | 0.54167 | 1 | Discussion with team on feedback from design draft, ideas on how to implement
2025-10-14 | 0.47917 | 0.52083 | 1 | Check in meeting 2, discussed improvements for final design plan
2025-10-17 | 0.54167 | 0.66667 | 3 | Team meeting, compiled research on possible components, discussed
2025-10-23 | 0.47917 | 0.5625 | 2 | Check in meeting 3, reviewed possible parts list
2025-10-23 | 0.79167 | 0.875 | 4 | Designed and built tinkercad demo with code
2025-10-23 | 0.66667 | 0.75 | 2 | Reviewed tinkercad for pre alpha build
2025-10-24 | 0.54167 | 0.66667 | 3 | Researched and found Kaggle dataset for car detection, yolo code for image recognition
2025-10-25 | 0.625 | 0.77083 | 3.5 | Created simple CNN for car detection
2025-10-28 | 11:00 | 12:30 | 1.5 | Check in meeting 4, discussed with team after to purchase parts
2025-11-02 | 17:00 | 19:00 | 2 | discussed work assignments and any parts we still need to order
2025-11-04 | 11:00 | 12:30 | 1.5 | Check in meeting 5, ordered Raspberry Pi, camera, and haptic sensors
2025-11-04 | 11:00 | 13:00 | 2 | team meeting, compiled research on possible components, discussed
2025-11-05 | 11:00 | 14:00 | 3 | team meeting to test radar sensor
2025-11-11 | 10:00 | 11:30 | 1.5 | Wrote email in lieu of check in 6, updating stakeholder on work the team completed and will present for prototype
2025-11-11 | 15:00 | 17:00 | 2 | integrated radar with distance sensor
2025-11-14 | 10:00 | 12:00 | 2 | switched radar sensor serial so that it works faster and detects more accurate with the arduino
2025-11-15 | 10:00 | 12:00 | 2 | worked with arduino and make the connections more organized to a smaller breadboard
2025-11-16 | 15:00 | 17:00 | 2 | practiced demo and slides for presentation
46.5

## Ana
Date | Time In | Time Out | Description of Work | Total Time
2025-10-01 | 19:30 | 22:00 | Researched existing solutions to cycling problem and ways to differentiate solution with our product | 2.5
2025-10-02 | 17:30 | 21:00 | Researched hardware components for helmet (potential sensors) | 2.5
2025-10-05 | 12:00 | 15:30 | Researched CNN model for image recognition and potential datasets to use for image detection | 3.5
2025-10-07 | 11:30 | 12:00 | Check in meeting 1, discussed design draft | 0.5
2025-10-09 | 12:00 | 13:00 | Discussion with team on feedback from design draft, ideas on how to implement | 1
2025-10-14 | 11:30 | 12:30 | Check in meeting 2, discussed improvements for final design plan | 0.5
2025-10-17 | 13:00 | 16:00 | Team meeting, compiled research on possible components, discussed | 3 | Total Time: | 46
2025-10-17 | 16:00 | 17:30 | Researched and added more components to possible component list individually | 1.5
2025-10-23 | 11:30 | 12:30 | Check in meeting 3, reviewed possible parts list | 1
2025-10-23 | 15:00 | 17:00 | Narrowed down parts list for pre-alpha build, reviewed Tinkercad and Arduino implementation | 2
2025-10-25 | 18:00 | 20:00 | Reviewed CNN code and researched ways to expand it for the prototype | 2
2025-10-28 | 23:30 | 12:00 | Check in meeting 4, ordered radar sensor and discussed ordering other parts | 0.5
2025-11-02 | 17:00 | 19:00 | Meeting with team, discussed work assignments and researched technical work to be completed | 2
2025-11-04 | 23:30 | 13:00 | Check in meeting 5, ordered Raspberry Pi, camera attachment for Raspberry Pi, and webcam in case; discussed plan to meet for Raspberry Pi and camera setup | 1.5
2025-11-07 | 13:00 | 16:00 | Gathered materials; set up Raspberry Pi and camera module; created simple script to make sure pictures/videos could be taken | 3
2025-11-10 | 13:00 | 16:30 | Researched more ways to improve ML model before testing (hyperparameters, etc.) | 3.5
2025-11-11 | 13:00 | 16:00 | Met with team and emailed stakeholder in lieu of Check in meeting 6; trained and tested ML model for vehicle image dataset | 3
2025-11-13 | 12:00 | 15:00 | Met with team and started working on the Onshape prototype for the helmet attachment. | 3
2025-11-14 | 15:30 | 17:30 | Sketched out attachable helmet module for the chosen helmet; reviewed Onshape tools and began creating module prototype in Onshape | 2
2025-11-15 | 12:00 | 15:30 | Completed 3D modeling of helmet module prototype on Onshape | 3.5
2025-11-16 | 14:00 | 18:00 | Ensured all components were functioning individually and together for demonstration; practiced prototype presentation | 4